## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
Toys Give Away |  | 20 | 2021-08-23 | 2021-09-11 | 2021-09-29
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design |  |  | 4
1.1 | Project Defination | 2021-08-23 | 2021-08-23 | 1
1.2 | Finish webpage | 2021-08-24 | 2021-08-25 | 2
1.3 | Project Design | 2021-08-26 | 2021-08-26 | 1
2 | Coding |  |  | 9
2.1 | Phase 1 | 2021-08-27 | 2021-08-30 | 4
2.2 | Phase 2 | 2021-08-31 | 2021-09-02 | 3
2.3 | Additional Features | 2021-09-03 | 2021-09-04 | 2
3 | Testing |  |  | 5
3.1 | Phase 1 Testing | 2021-09-05 | 2021-09-05 | 1
3.2 | Modification /Any changes | 2021-09-06 | 2021-09-06 | 1
3.3 | Phase 2 Testing | 2021-09-07 | 2021-09-07 | 1
3.4 | Modification /Any changes | 2021-09-08 | 2021-09-08 | 1
3.5 | Final Testing | 2021-09-09 | 2021-09-09 | 1
4 | Documentation |  |  | 2
4.1 | User Guide | 2021-09-10 | 2021-09-10 | 1
4.2 | Presentation | 2021-09-11 | 2021-09-11 | 1

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Team member
| Member Name | Shubham Bachkar
| PRN No | 210543181012
| Description | Back End SpringBoot
2 | Role | Team member
| Member Name | Sachin Patil
| PRN No | 210543181064
| Description | Database MySQL
3 | Role | Team Leader
| Member Name | Ajay Sheelwant
| PRN No | 210543181097
| Description | Over all project
4 | Role | Team member
| Member Name | Shankar Sure
| PRN No | 210543181110
| Description | Front End React